## Sheet1
Change Request ID | Date Submitted | Submitted by | Description | Reason/Justification | Impact Analysis | Priority | Approval Status | Approved by & date
1 | 2026-06-12 | Exam Controller | Online exam Registration for students | Students struggle with manual fee submission, reduce queues.Reduce paperwork | Core module, need database, login/signup UI, Exam Registration from UL | High | Approved | Project Manager 13-Jun-26
2 | 2026-06-11 | Project Manager | Need Admin dashboard, generate report for studentsgrade, download or export excel format | Admin exam controller needs reports ithout IT help | Admin dashboard, export/download business logic | medium | Approved | Project Manager 13-Jun-27
3 | 2026-06-10 | IT Security Lead | Implement two-factor authentication (2FA) for teacher and admin login | Prevent unauthorized access to student grades and exam data; university had data breach concerns | Add OTP verification step, integrate with email/SMS gateway, extra testing for login security | High | Approved | Project Manager 12-Jun-28
4 | 2026-06-09 | Student Representative | Add "Forgot Password" and password reset via email | Students often forget passwords and cannot contact support immediately | Requires email service integration, password reset link generation, secure token expiry logic | Medium | Approved | Project Manager 11-Jun-29